## version 1.0 - 928
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | Team leader | 12/20 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more team members add the class | 1 | 3 | 3 | 45 | Team leader | 2023-09-28 | Redefine the project scope if necessary, and assign the tasks to other team members. | No new member | Closed
| Lack of motivation or responsibility | One or more members derail or fall behind the tracking | 2 | 5 | 3 | 12 | Team leader | 2023-12-20 | Personal Communication, Task Reallocation | Aware of risk | Open
Communication | duplicate work | team members unintentionally replicate tasks, leading to wasted effort and resources. | 3 | 5 | 3 | 9 | Team leader | 2023-12-20 | Implement a process for tracking ongoing tasks to minimize the likelihood of duplication. Encourage team members to communicate. | Aware of risk | Open
| worked on wrong components | working on the wrong project components or features | 3 | 4 | 3 | 18 | Team leader | 2023-12-20 | Maintain a well-organized project documentation system that includes clear specifications and task assignments. Conduct regular code reviews to ensure that team members are working on the correct components and adhering to project requirements. | Aware of risk | Open
| useless work | Useless work refers to efforts that do not contribute to project goals or requirements | 2 | 4 | 2 | 16 | Team leader | 2023-12-20 | Prioritize tasks based on their contribution to project objectives and requirements. | Aware of risk | Open
| inconsistent work | Inconsistent work results from variations in the quality and approach of team members' contributions | 4 | 3 | 3 | 18 | Team leader | 2023-12-20 | Implement coding standards and guidelines to maintain consistency in code quality and structure. Conduct regular code reviews | Aware of risk | Open
Requirements | unclear requirements | ambiguous choice of word, or non-descriptive sentence can lead to misunderstandings, misinterpretations, and ultimately, the development of incorrect or incomplete features | 2 | 5 | 1 | 4 | Design Lead, Team Lead | 2023-10-06 | Maintain a well-documented requirements specification. Regular meetings | Aware of risk | Open
| scope creep | uncontrolled expansion of project scope beyond the initially defined boundaries | 3 | 2 | 4 | 48 | Design Lead, Team Lead | 2023-12-20 | formal change control process to evaluate and approve any proposed changes to project scope | Aware of risk | Open
| constant requirements changes | Frequent changes to project requirements during development | 4 | 2 | 3 | 24 | Design Lead | 2023-12-20 | Set clear change request submission and approval procedures. | Aware of risk | Open
Management | improper task assignments | tasks being assigned to team members who may not have the required skills or expertise | 5 | 5 | 2 | 2 | Team leader, FE/BE Lead | 2023-12-20 | Assign tasks based on team members' competencies and expertise Maintain open channels for team members to communicate | Aware of risk | Open
| improper planning | inaccurate estimations, inadequate resource allocation, or unrealistic timelines | 5 | 4 | 1 | 2 | Team leader, FE/BE Lead | 2023-12-20 | A detailed project plan that includes comprehensive timelines, resource allocation, and deliverables. Regularly review and update the project plan | Aware of risk | Open
| lack of management skills | inefficient coordination, poor decision-making, and difficulties in managing project resources and timelines. | 5 | 5 | 1 | 1 | Team leader, FE/BE Lead | 2023-12-20 | Continuously evaluate and enhance project management practices | Aware of risk | Open
Technology competence | Not familiar with the framework used | Team members' unfamiliarity with the chosen technology framework can slow down development, increase the likelihood of errors, and require additional time for learning and adaptation | 5 | 5 | 1 | 1 | FE/BE Lead, Backup Programmer | 2023-12-20 | Encourage team members to explore online resources and documentation related to the framework. | Aware of risk | Open
| Not familiar with the programming language used | proficiency in the programming language selected for the project can lead to coding challenges, decreased productivity, and potential code quality issues | 5 | 5 | 1 | 1 | FE/BE Lead, Backup Programmer | 2023-12-20 | Encourage team members to practice coding in the selected language and seek assistance when needed. Conduct code reviews to identify and address language-specific issues. | Aware of risk | Open
| Not familiar with unit testing | inadequate test coverage, reducing the effectiveness of quality assurance efforts and potentially leading to undetected issues | 5 | 4 | 1 | 2 | QA Lead, Backup QA, Config. Lead | 2023-12-20 | Encourage team members to implement unit tests in their code and share knowledge about testing frameworks. Establish a review process to ensure the proper implementation of unit tests. Monitor test coverage and quality to track progress. | Aware of risk | Open
| Other technology incompetence | unfamiliar tools, libraries, or best practices | 3 | 3 | 3 | 27 | Team members | 2023-12-20 | Encourage team members to seek assistance or mentorship from colleagues | Aware of risk | Open
| Not familiar with Git | difficulties in code collaboration, version management, and project tracking | 1 | 5 | 3 | 15 | Team members | 2023-12-20 | Encourage team members to practice Git usage in a collaborative environment. Monitor Git usage and address issues or questions promptly. Use pull/push request template form. | Aware of risk | Open
Design and implementation | Improper design | difficult to maintain, extend, or adapt to changing requirements or scalability | 4 | 4 | 1 | 4 | Team Lead, Design Lead | 2023-12-20 | Conduct design reviews with team members to ensure alignment with project goals. | Aware of risk | Open
| improper technology stack | compatibility issues, performance bottlenecks, and challenges | 3 | 5 | 3 | 9 | Team Lead, Design Lead, FE/BE Lead, DevOps Lead | 2023-12-20 | Maintain a technology stack documentation and update it as needed. Monitor the performance and compatibility of the chosen stack. | Aware of risk | Open
| Messy code | unstructured code can hinder code readability, maintainability, and collaboration among team members. | 4 | 3 | 3 | 18 | Team members | 2023-12-20 | Coding standards and best practices within the team. Conduct regular code reviews Encourage documentation and comments to enhance code clarity | Aware of risk | Open
Testing | Not enough testing | Inadequate testing, including insufficient test coverage and depth | 4 | 5 | 3 | 6 | QA Lead, Backup QA, Config. Lead, DevOps Lead | 2023-12-20 | Develop a comprehensive testing strategy that includes unit, integration, and system testing. Automated testing frameworks Regular test result review | Aware of risk | Open
Integration and deployment | Not enough time for integration and deployment | Time constraints for integration and deployment can lead to rushed processes, potentially causing errors, issues, or delays | 5 | 5 | 2 | 2 | QA Lead, DevOps Lead | 2023-12-20 | Prioritize integration and deployment activities in the project plan. Implement continuous integration and deployment (CI/CD) pipelines to streamline. | Aware of risk | Open