## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration. | [5 empty] | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 9/14/2023 - 9/28/2023 | Project write-up proposal/ Team work-distribution, User requirement | None Tech issue so far | None non-tech issue so far | Next week : 1.User Requirement analysis 2.Final UXUI Design 3.BE Kickstart -> Schema + Login/Logout 4.FE Kickstart -> UI User Login/Logout/Home | 0 | 0 | 0 | 0 | 0 | 35.5 | 31.5 | 4 | 16.5 | 4.5 | 0 | 2 | 0 | 5 | 4.5 | 4.5
1 | 09/29 - 10/05 | Brought domain + Setup Project folder/structure + DB Schema + Setup Webpage | None Tech issue so far | None non-tech issue so far | 1.User Flow and Stories 2.Landing Page 3.Login Page 4.DB Setup | 1 | 2 | 0 | 0 | 0 | 42.5 | 38 | 4.5 | 16 | 4 | 4.5 | 5.5 | 0 | 5 | 1 | 2
2 | 10/06 - 10/12 | Implement BE and First Version FE | None Tech issue so far | First Version FE not quite right | 1.Main Page 2.DB Setup / BE Setup 3.Login Page 4.Final Design | 1 | 2 | 1 | 0 | 0 | 47.5 | 43 | 4.5 | 16.5 | 1 | 3.5 | 14.5 | 0 | 5 | 0 | 1
3 | 10/13 - 10/19 | Implement BE/Auth() and Second Version FE | Auth() need to be fix | Second Version FE better but overall need change for UI | Next Week : 1.Fix Authentication 2.Email Verification Signup 3.UI Code Incorporate 4.Commenting 5.Browsing | 3 | 4 | 1 | 0 | 0 | 40.5 | 36 | 4.5 | 8.5 | 1 | 0.5 | 9.5 | 1 | 3.5 | 0 | 5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Theerarun (Steve)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader, Backup Frontend
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6.5 | 4.5 | 2 | 0 - Learn git 1 - Define user requirement 5 - Team Management 6 - Setup Git 7 - Presentation/Writeup | 0.5 | 1 | 0 | 0 | 0 | 1 | 0.5 | 1.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. First-meetup is so good, we are missing people and late 2. communication is not enough. task assignment is not clear | 1. keep a reminder and confirm 2. Send task assignments to confirm with members and set up task-board | 0 - Learn Github Project/Issues 0 - Brushup React/JS 1 - Final User Requirement 2 - Work with Design Lead for UXUI 5 - Follow up each team 6 - Setup config/ implementation environment | 8
3 | 09/29 - 10/05 | 5.5 | 4 | 1.5 | 1-User Stories Documentation 1-User Requirement Analysis 2-UI Design Research 5-Team Management | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1.Write and Analyse User Flow and Stories 2.Research UI Design 3.Setup meeting and communication | 1.We tried to have a weekly in-person meetup so that we can have a clear communication over issues but it never happens as a whole group | 1. Try to adjust or reschedule to the time that everyone can really make it | 0 - Brushup React/JS 1- Final User Stories 2 - Work with Design Lead for UXUI | 5
4 | 10/06 - 10/12 | 6 | 4.5 | 1.5 | 0-Learn about React/JS 1-UI Requirement Analysis 2-UI Design 5-Team Management | 0.5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1.Final User Flow and Stories 2.Design UI with Design Lead 3.Setup meeting and communication | 1.The Frontend coding seems off the UI, but we fix it | - | 0 - Brushup React/JS 7 - Project Documentation | 5
5 | 10/13 - 10/19 | 5.5 | 4 | 1.5 | 0-Learn about React/JS 5-Team Management 7-Presentation/Writeup | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1. Write up SDD + Presentation Slides 2. Participate in Iteration 1 presentation 3. Setup Meeting and communication | 1.FE/BE connections are not perfect, but we manage to fix | 1.Next week will need to incorporate UI Design to the coding | 0 - Brushup React/JS 2 - Final UI Design 3 - Implement UI to FE/coding | 6

## Subhajit (Jeet)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 09/14-09/27 | 8.5 | 7 | 1.5 | 0 - learned git and unit test cases, read several tutorials 1 - define high level requirements, 5 - make Backend Dev plan, send reminders to team members, 6 - set up git, local development 7 - research similar products, prepare presentation, did research on how other products work | 3.5 | 1 |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
3 | 09/29 - 10/05 | 5.5 | 4 | 1.5 | 2 - Designed basic db schema for post API 6 - Bought domain and set- it up 7 - research about Auth0 |  |  | 2 |  |  |  | 1 | 1 | 1. Designed DB schema 2. Bought domain to make it live on the internet and set it up on the server | 1. Designing DB schema for such large project was hard and had to do a lot of project 2. Communication among Backend team members was little unclear | 1. Finished DB schema with other backend team members 2. started doing a small backend team stand-up meeting, so everyone understands their responsibilities | 0 - Start implementing Auth0 1 - Start designing user post API | 6
4 | 10/06 - 10/12 | 8.5 | 7 | 1.5 | 0 - Learn more about Auth0 and how to use it 2 - Fixed some DB schema desgin flaw 3 - Started implementing Django application and folder structure | 2 |  | 2 | 3 |  |  |  |  | 1. Gave other backend team member a quick workshop about DB schema and REST apis 2. Assigned tasks to backend team members to work on 3. Finished set-up backend app with Django | 1. had to slow down the development because of diverse skill level of other team members. 2. It took a lot of time to do research on Auth0 and how to integrate with our app | 1. Developement speed is on right space now 2. Understood basics of Auth0 and how to use it | 1. Implementation of Auth0 to perform login and logout 2. Deployment to server to make it live online | 6
5 | 10/13 - 10/19 | 7 | 5.5 | 1.5 | 0 - Learned how to implement Auth0 3 - Implemented Auth0 4 - Performed manual Testing on Login and Logout 5 - Had a meeting about our deliverables and our tech backlogs | 1 |  |  | 3 | 1 | 0.5 |  |  | 1. Fixed last minutes bug for demo 2. Helped creating presentation slides 3. Participated in class presentation | 1. Auth0 integration is not working with backend APIs. 2. Deployment issue, unexpected error 3. Issue connecting server with clients | 1. Changed plan for Auth0, integrated in client side of code 2. Deployement issue is still there, need more time to debug it and fix it 3. Server - client connection is still there, need time to fix it | 1. Finish user post API 2. Designed standard system to deployment, no issue will occur in last time 3. Set-up Github auto merge, deployement test check tools 4. Set-up Staging, so we don't have to test on production | 12

## Aishwarya
Your Lead Roles: Configuration Management/ Product Management
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 09/22-09/27 | 7.5 | 5.5 | 2 | 0 - Learn git 5 - Product Management 6 - Setup Git and github version control tools, other specific tools like IDE,CI/CD and branching features 7 - Presentation, researched similar products. | 3 |  |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. keep a reminder and confirm 2. complete assignments and tracking team members | 0 - learn Django 1 - Implement while learning 2 - Brush up Python 5 - Complete assigned task | 8
3 | 09/29 - 10/05 | 8.5 | 6.5 | 2 | 0-Learn Reactt, Brushed up Python and earn Django 1-User Stories 2-Design Landing page 7-Research Landing page | 5 | 0.5 | 0.5 |  |  |  |  | 0.5 | 1.Write User Stories 2.Research Landing page | 1. Unclear with concepts of Django 2. Communication among Backend team members was little unclear |  | 1. Make clear about Django concepts 2. Complete task assignments 3. Developing Landing Page | 8
4 | 10/06 - 10/12 | 8.5 | 7 | 1.5 | 0. Brushed up Python, learn Django 3. Added content to Landing Page 7. Finalized content for Landing Page | 5 |  |  | 1 |  |  |  | 1 | 1. Created the Landing Page |  | 1. Completed the Landing Page 2. Learning Django but not completely familiar with it. 3. Write user stories for iteration 1 | 1-Write user stories( Non functional) 2-Continue learning Django | 8
5 | 10/13 - 10/19 | 5 | 4 | 1 | 0. Django tutorial 1. User Stories 7. User stories write-up(Non-functional) | 2 | 0.5 | [5 empty] | 1 | 1. Wrote the Non functional User Stories | No prior experience in deployment with API | 1. Done writing user stories( Non functional) 2.Write the content for Email verification 3.Research on 'Resend' an Email API | 1-Write the content for Email verification 2-Research and write content on 'Resend' an Email API and go through API tutorials. | 6

## Nidhi
Your Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6 | 4 | 2 | 0. Learn Git and Django 6. Set up git 7. SPPP writeup | 3 | [5 empty] | 0.5 | 0.5 | 1. Write 1 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Not Familiar with Django 2. Not familiar with Cypress | 1. Finish going through Django tutorials 2. Complete task assignments 3. Familiarize myself with Cypress 4. Start implementing Django while learning | 0 - Continue to learn Django 1 - Implement while learning 2 - Brush up Python 3 - Familiarize myslf with Cypress 4 - Complete assigned task | 8
3 | 9/29-10/5 | 8.5 | 6.5 | 2 | 0. Learn Django, Brushed up Python, learn React 1. User Stories 2. UI for Landing Page 7. Research on landing page and Content for Landing page | 5 | 0.5 | 0.5 |  |  |  |  | 0.5 |  | 1. Not entirely familiar with React but making progress | 1. Finish going through Django tutorials 2. Complete task assignments 3. Familiarize myself with Cypress 4. Start coding for Landing Page | 0 - Continue to learn Django 1 - Implement while learning 2 - Brush up Python 3- Create the Landing Page 4- Start going through Cypress tutorials | 8
4 | 10/6-10/12 | 8.5 | 7.5 | 1.5 | 0. Brushed up Python, learn React, Cypress Tutorial 2. Update design for Landing Page 3. Landing Page | 4.5 |  | 0.5 | 2 |  |  |  |  | 1. Coding for the Landing page | 1. Currently learning Cypress by following tutorials, but not yet completely familiar with it 2. Created the Landing page but needs to be updated later according to the final design | 1. Started going through Cypress tutorials 2. Completed the Landing Page 3. Finished with the Django tutorials 4. Write user stories for iteration 1 | 0 - Continue with Cypress tutorials 3- Write the user stories(Functional) and their Acceptance Criteria | 4
5 | 10/13-10/19 | 5 | 4 | 1 | 0. Cypress tutorial 1. User Stories 7. Class diagram, User stories write-up (Functional and Acceptance Criteria) | 2 | 0.5 | [5 empty] | 1.5 | 1. Wrote the User Stories(Functional) and their Acceptance Criteria. 3. Participated in Iteration 1 presentation | 1. No prior experience in writing and deploying APIs | 1. Finish going through Cypress tutorials 2. Done writing user stories(Functional) and Acceptance Criteria 3. Write the content for Verificaton Email 4. Research on 'Resend' an Email API | 0 - Finish going through Cypress tutorial and start testing 1 - Go through API tutorials 2 - Write the Verification email content 3- Research on 'Resend' an email API | 6

## Vedant
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/21 - 9/28 | 5.5 | 4.5 | 1 | 0 - learn git and react, started learning through a playlist 1 - Stated high level requirements 6 - set up git 7 - Prepared the two parts in spp document for overview and requirements | 3 | 0.5 |  |  |  |  | 0.5 | 0.5 | 1. Wrote 2 sections of SPPP 2. Set up git, commit a test message on git | 1. not familar with React framework, it's been a couple of years since I did programming so catching up to it | 1) Started with a playlist on YouTube for react, able to write a very basic code | Continue to learn React and get more familiar with it. | 7
2 | 9/29 - 10/5 | 5 | 4 | 1 | 0 - Learning React 2 - Designing UI mockup 3 - Started coding for basic login page | 3 |  | 0.5 | 0.5 | [5 empty] | 1. Not entirely familiar with react but catching up pretty quick. | 1) Able to write a basic code, planning to work on the login page implementation | 1) Continue to learn React and work on User story and design | 6
3 | 10/6 - 10/12 | 5 | 4 | 1 | 0- Learning React (Built small programs) 3 - Coded the login page | 1.5 |  |  | 2.5 |  |  |  |  | 1 - Coding the login page | 1 - Faced some complexities with the login page but gradually looked for tutorials | 1 - Able to make basic programs, learning more about React and learning to code more efficiently | 1 - Will work on UI and wireframe again for better design | 5
4 | 10/13 - 10/19 | 6.5 | 5.5 | 1 | 0 - Learning React and moved to better programs 2 - Designed mockups for other pages 3 - Recoding the login page as a pop up to the main landing page 7 - class diagram help | 1 |  | 0.5 | 3.5 |  |  |  | 0.5 | 1 - Design mockups for other pages 2 - Redoing the login page as a pop up to the main landing page | 1 - Trying to connect the login page as a pop up to main landing page, working on it currently. | 1 - Will complete the login page as a pop up to the main landing page | 1 - Learn react with more modules from the udemy course I am learning from. | 5

## Xiancheng Yin(Xanthus)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 8 | 6.5 | 1.5 | 0 - learn git and django, read several tutorials 1 - define high level requirements through similar products, 5 - team meeting 6 - set up git 7 - research similar products, prepare presentation | 1.5 | 1.5 |  |  |  | 1.5 | 0.5 | 3 | 1. suggestions made by comparing similar products for high-level requirements and functionalities 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 0. not familar with Django framework, tried learning resources to see which is good 2. Sometimes communication is not clear. Task assignments is not clear. | 0. finish Django tutorial in 2 weeks, be able to create Djano project in online courses next week 2. Enforce communication, confirm everything. | 0 - continue to learn Django 1 - continue to define product name/ requirements 3 - seting up domain and Backend Code(documentation if time is permit) cowork with jeet | 7
3 | 9/29 - 10/5 | 8 | 6.5 | 1.5 | 0 - learn domain and Django and related things 1 - continue to define product name/ requirements 3 - seting up domain and Backend Code(documentation if time is permit) cowork with jeet 5 - team meeting, BE team meeting; | 1.5 | 1 |  | 2 |  | 2 |  |  | cowork with jeet seting up things | no issue |  | 0 - learn database connecting related python; 3 - implementing settings.py, models.py, routers.py 5 - team meeting, BE team meeting; | 6.5
4 | 10/6 - 10/12 | 8 | 6.5 | 1.5 | 0 - learn supabase and django; 3 - implementing supabase, create account, setting up, create tables and testing data; 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | Set up Supabase account, created tables according to the attributes and functions for classes | no issue |  | 0 - learn database connecting related python; 3 - implementing settings.py, models.py, routers.py 5 - team meeting, BE team meeting; | 6.5
5 | 10/13 - 10/19 | 8 | 6.5 | 1.5 | 0 - learn database connecting related python; 3 - implementing settings.py, models.py, routers.py 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | Created settings.py, models.py, routers.py files, | tried several tutorials, solved some problems such as "SupabaseException("Invalid API key")" but still cannot update database through python | still didn't get fully connected to be able to use. Tried to contact back-end leader and discuss. Will try different alternatives. | 0 - learn different alternative databases 3 - implementing new database 5 - team meeting, BE team meeting; | 6.5

## Chenyang Lyu
Your Lead Roles: FE Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 5 | 5 | 1 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 2 | 1 |  |  |  |  | 1 | 1 | "1. make the ux frame 2. submit git files 3. Participate in Iteration 0 presentation" | the task assignment is not very clear | finish the ux design | -2 doing the ux design | 6
3 | 9/29 - 10/5 | 8 | 6.5 | 1.5 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 1.5 | 1 |  | 2 |  | 2 |  |  | Keep doing the ux design | no issue |  | 6- set up environment | 6.5
4 | 10/6 - 10/12 | 8 | 6.5 | 1.5 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 1.5 |  |  | 3 |  | 2 |  |  | doing sign up page front end code | no issue |  | 7- code writing | 6.5
5 | 10/13 - 10/19 | 8 | 6.5 | 1.5 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 1.5 |  |  | 3 |  | 2 |  |  | finish sign up page and main page of the front end | no issue |  | 7-code writing | 6.5

## studentName-Template
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6