## Summary-GroupIterationProgress
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration. | [5 empty] | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 9/14/2023 - 9/28/2023 | Project write-up proposal/ Team work-distribution, User requirement | None Tech issue so far | None non-tech issue so far | Next week : 1.User Requirement analysis 2.Final UXUI Design 3.BE Kickstart -> Schema + Login/Logout 4.FE Kickstart -> UI User Login/Logout/Home | 0 | 0 | 0 | 0 | 0 | 35.5 | 31.5 | 4 | 16.5 | 4.5 | 0 | 2 | 0 | 5 | 4.5 | 4.5
1.1 | 09/29 - 10/05 | Brought domain + Setup Project folder/structure + DB Schema + Setup Webpage | None Tech issue so far | None non-tech issue so far | 1.User Flow and Stories 2.Landing Page 3.Login Page 4.DB Setup | 1 | 2 | 0 | 0 | 0 | 42.5 | 38 | 4.5 | 16 | 4 | 4.5 | 5.5 | 0 | 5 | 1 | 2
1.2 | 10/06 - 10/12 | Implement BE and First Version FE | None Tech issue so far | First Version FE not quite right | 1.Main Page 2.DB Setup / BE Setup 3.Login Page 4.Final Design | 1 | 2 | 1 | 0 | 0 | 47.5 | 43 | 4.5 | 16.5 | 1 | 3.5 | 14.5 | 0 | 5 | 0 | 1
1.3 | 10/13 - 10/19 | Implement BE/Auth() and Second Version FE | Auth() need to be fix | Second Version FE better but overall need change for UI | Next Week : 1.Fix Authentication 2.Email Verification Signup 3.UI Code Incorporate 4.Commenting 5.Browsing | 3 | 4 | 1 | 0 | 0 | 40 | 35.5 | 4.5 | 10 | 1 | 0.5 | 14.5 | 1 | 3.5 | 0 | 5
1 | 09/29 - 10/19 | Brought domain + Setup Project folder/structure + DB Schema + Setup Webpage Implement BE and First Version FE Implement BE/Auth() and Second Version FE | Auth() need to be fix | Second Version FE better but overall need change for UI | Immediate Tasks User Flow and Stories: Outline the user journey and create user stories for the application. Web Pages Development: Design and develop the Landing Page. Create the Login Page. Develop the Main Page, focusing on finalizing the design. Database and Backend Setup: Initial setup of the Database (DB). Backend (BE) setup and configuration. Next Week's Tasks Authentication and Security: Fix issues related to Authentication. Implement Email Verification for Signup. Frontend Integration and Refinement: Incorporate UI code into the project. Comment and document code for clarity and maintainability. User Experience Enhancement: Improve and refine the Browsing feature for better user engagement. | 5 | 8 | 2 | 0 | - | 130 | 116.5 | 13.5 | 42.5 | 6 | 8.5 | 34.5 | 1 | 13.5 | 1 | 8
2.1 | 10/20 - 10/26 | FE : Implement Login/Signup/MainPage/Marketplace BE : Implement token | Connection FE/BE not settle | Marketplace page misconcept | Next Week : 1.Rework Authentication 2.Marketplace UI Setup 3.Marketplace Need rework 4.Database connection 5.Postdetail UI | [5 empty] | 43 | 38.5 | 4.5 | 16 | 4 | 1 | 9 | 0.5 | 5 | 1 | 2
2.2 | 10/27 - 11/02 | FE : Implement Marketplace rework + PostDetail BE : Implement User DB and Login-Api | Issue connecting web app client with backend JWT decode issue with Django | None non-tech issue so far | Next Week : 1.Setup FE/BE connection 2.About/Contact UI 3.Comment/Search Feature 4.Start writeup testcase 5.Configure server | [5 empty] | 42 | 37.5 | 4.5 | 10 | 4 | 1 | 15 | 3 | 3 | 1 | 0.5
2.3 | 11/03 - 11/08 | FE : Implement About/Contact/UserProfile page BE : Implement new Authentication + Config server to receive requests QA: Write up, and Start testing some. Deployment: Explore Vercel | Some issue with frontend code API request that is not going though banckend | None non-tech issue so far | Next Week : 1.FE/BE connection needs to be connect 2.Colored ui for main feature(homepage/marketplace) 3.UserProfile Edit feature 4.Search Optimization Implementation 5.Direct Message implementation | [5 empty] | 43 | 38.5 | 4.5 | 0.5 | 0.5 | 0.5 | 22 | 5 | 1.5 | 2 | 3.5
2 | 10/20 - 11/08 | Frontend Development: Implement Login, Signup, MainPage, and Marketplace features. Rework the Marketplace and implement the PostDetail feature. Develop About, Contact, and UserProfile pages. Backend Development: Implement token handling for secure authentication. Set up User Database and Login API for user authentication and data management. Implement a new authentication system and configure the server to receive requests. Quality Assurance: Write up initial test cases and plans. Start testing the implemented features, focusing on both frontend and backend components. Deployment: Explore deployment options and strategies, with an initial focus on using Vercel as the deployment platform. | Issue connecting web app client with backend JWT decode issue with Django | None non-tech issue so far | Next Week : 1.FE/BE connection needs to be connect 2.Colored ui for main feature(homepage/marketplace) 3.UserProfile Edit feature 4.Search Optimization Implementation 5.Direct Message implementation 6.Full Testing | [5 empty] | 128 | 114.5 | 13.5 | 26.5 | 8.5 | 2.5 | 46 | 8.5 | 9.5 | 4 | 6
3 | 11/09 - 12/11 | FE : User Profile Edit/ Direct Message/ Search Filters / Login/Register Improvement BE : Backend Infra Deployment, Backend Testings QA : Manual Testing, Components Testing, E2E Testing, Automation Testing Deployment : Webapp Deployment | Some issue with frontend code API request that is not going though banckend - > Resolved. Prior Cypress does not work but resolved. | None non-tech issue so far | - | [5 empty] | 38.5 | 34 | 4.5 | 1 | 1.5 | 1 | 20 | 4 | 5 | 3 | 0
[11 empty] | 38 | 33.5 | 4.5 | 2 | 0 | 2 | 17.5 | 10 | 4 | 1 | 4
[11 empty] | 52 | 47.5 | 4.5 | 0.5 | 2 | 2.5 | 14.5 | 6.5 | 5 | 3.5 | 9
[11 empty] | 31 | 26.5 | 4.5 | 0 | 0 | 2 | 9 | 2 | 1 | 3 | 6
[11 empty] | 13.5 | 9 | 4.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7
3 | 11/09 - 12/11 | FE : User Profile Edit/ Direct Message/ Search Filters / Login/Register Improvement BE : Backend Infra Deployment, Backend Testings QA : Manual Testing, Components Testing, E2E Testing, Automation Testing Deployment : Webapp Deployment | Some issue with frontend code API request that is not going though banckend - > Resolved. Prior Cypress does not work but resolved. | None non-tech issue so far |  |  |  | 17 | 84 |  | 173 | 150.5 | 22.5 | 3.5 | 3.5 | 7.5 | 61 | 22.5 | 16 | 11.5 | 26

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Theerarun Tubnonghee (Steve) | Write up SPPP - Management | - | Write up SDD-Overview | Write up STD-Testing Overview | FE Overview | Login/Register/UpdatePost/UserProfile/EmailRestriction/DirectMessage/Homepage | Overview Results | - | Overall Communication and Team Manament | Helm of communication and documentation
Subhajit (Jeet) | Write up SPPP - Related Work | Keep Track BE part | Write up SDD-BE Part | Unittest | BE Overview | Backend API | BE Testing | Setup Database | Backend Related Leading communicator | Help setting up Backend Standards and Backbone
Aishwarya | Write up SPPP - Configuration | - | Write up SDD-BE Part | Unittest | Project Management/Config | Backend API | BE Testing | Configure github and project | Github Standards communicator | Backend/Misc. problem solver
Vedant | Write up SPPP - Requirements | - | Write up SDD-UI Design | Unittest | Demo Showcase | Login/Register/Marketplace/CreateDeleteProduct/Search/Filter/DirectMessage/UI | FE Testing | - | Frontend communicator | Frontend bug fixers
Xiancheng (Xanthus) | Write up SPPP - Related Work | - | Write up SDD-BE Part | Unittest | Security and Deployment | Backend API | BE Testing | Deployment | DevOp related communicator | DevOps handler
Chenyang (Nick) | Write up SPPP - Frontend Draft | - | Write up SDD-UI Design | Unittest | FE Implementation | Main UI/Direct Message/About/ContactUs/Marketplace | FE Testing | - | Frontend communicator | Kickoff Frontend Structure code
Nidhi | Write up SPPP - Code Review/Testing | Keep Track FE part | Write up SDD-BE Part | Write up STD-Testing | Testing | Testing Code Cypress | FE Testing | - | Testing management and communicator | Handling Most of Testing

## Theerarun (Steve)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader, Backup Frontend
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6.5 | 4.5 | 2 | 0 - Learn git 1 - Define user requirement 5 - Team Management 6 - Setup Git 7 - Presentation/Writeup | 0.5 | 1 | 0 | 0 | 0 | 1 | 0.5 | 1.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. First-meetup is so good, we are missing people and late 2. communication is not enough. task assignment is not clear | 1. keep a reminder and confirm 2. Send task assignments to confirm with members and set up task-board | 0 - Learn Github Project/Issues 0 - Brushup React/JS 1 - Final User Requirement 2 - Work with Design Lead for UXUI 5 - Follow up each team 6 - Setup config/ implementation environment | 8
3 | 09/29 - 10/05 | 5.5 | 4 | 1.5 | 1-User Stories Documentation 1-User Requirement Analysis 2-UI Design Research 5-Team Management | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1.Write and Analyse User Flow and Stories 2.Research UI Design 3.Setup meeting and communication | 1.We tried to have a weekly in-person meetup so that we can have a clear communication over issues but it never happens as a whole group | 1. Try to adjust or reschedule to the time that everyone can really make it | 0 - Brushup React/JS 1- Final User Stories 2 - Work with Design Lead for UXUI | 5
4 | 10/06 - 10/12 | 6 | 4.5 | 1.5 | 0-Learn about React/JS 1-UI Requirement Analysis 2-UI Design 5-Team Management | 0.5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1.Final User Flow and Stories 2.Design UI with Design Lead 3.Setup meeting and communication | 1.The Frontend coding seems off the UI, but we fix it | - | 0 - Brushup React/JS 7 - Project Documentation | 5
5 | 10/13 - 10/19 | 5.5 | 4 | 1.5 | 0-Learn about React/JS 5-Team Management 7-Presentation/Writeup | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1. Write up SDD + Presentation Slides 2. Participate in Iteration 1 presentation 3. Setup Meeting and communication | 1.FE/BE connections are not perfect, but we manage to fix | 1.Next week will need to incorporate UI Design to the coding | 0 - Brushup React/JS 2 - Final UI Design 3 - Implement UI to FE/coding | 6
6 | 10/20 - 10/26 | 4.5 | 3 | 1.5 | 0-Learn about ReactJS UI 5-Team Management 6-Review Pull Request/ Codes 7-Presentation/Writeup | 0.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 1.Review pull-request from be/fe teams 2.Update SDD | 1.FE raise pull requests to main, which is not corrcts | 1.Git Pull request contribution is documented | 0 - Learn more of ReactJS | 4
7 | 10/27 - 11/02 | 4.5 | 3 | 1.5 | 0-Learn about ReactJS unittest 5-Team Management 6-Review Pull Request/ Codes 7-Presentation/Writeup | 0.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 1.Review pull-request from be/fe teams 2.Update SDD | 1.Did not contribute to the team much this iteration | 1.Contribute more next week | 0 - Learn more of ReactJS Testing 3 - Start some code/refractor 7 - Prepare for It2 Presentation | 8
8 | 11/03 - 11/08 | 9 | 7.5 | 1.5 | 0-Learn about ReactJS unittest 3-Refractor Code 4-Write unittest for Marketplace 5-Team Management 6-Review Pull Request/ Codes 7-Presentation/Writeup | 0.5 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 1.Review pull-request from be/fe teams 2.Refractor Marketplace code 3.Write Unittest for Marketplace 4.Writeup STD + Presentation Slides | 1.Cannot get unittest to run 2.After review codes, we need a lot of refractoring 3.Project is behind schedule | 1.Reaching out to teammates QA lead 2.Meeting with Front-end team and set code standards 3.We should lean down the project scope to meet deadline | 0 - Learn more of tailwindcss to finalize the colored front-end ui 3 - Refractor main feature 4 - Test unittests for frontend 5 - Setup in-person meeting | 8
9 | 11/09 - 11/17 | 4.5 | 3 | 1.5 | 5 - Team Management Followup 6 - Review Pull Request/ Codes 6 - Set up FE/BE connection to Server -> write Readme.md | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1.Review pull-request from be/fe teams 2.Setup FE/BE on my local -> write readme.md | Comment needs to be dropped and change to other feature | change to direct message feature | 2 - Design Direct Message Design | 5
10 | 11/18 - 11/24 | 4.5 | 3 | 1.5 | 2 - Design Direct Message UI 5 - Team Management Followup 6 - Review Pull Request/ Codes | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | Design direct message design | Taking A week-off for thanksgiving | Plan to final change for user profile edit feature | 2,3 - User Profile Edit feature | 5
11 | 11/25 - 11/30 | 6.5 | 5 | 1.5 | 2 - Design User Profile Edit 3 - Implement User Profile Edit 5 - Team Management Followup 6 - Review Pull Request/ Codes | 0 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | redesing user profile edit dialog popup box | Some error due to the new feature | Plan to final change for minor change/improvement for register/login | 2,3 - Login/Register Minor change to enforce strong password/ edu | 6
12 | 12/1 - 12/7 | 7.5 | 6 | 1.5 | 3 - Web socket for the direct message feature with Nick and steve, worked on bug fixes 3 - Minor Bugs for login/register/user component/page 5 - Team Management Followup 6 - Review Pull Request/ Codes 7 - Prepare Presentation for Iteration 3 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 2 | Work closely with Frontend team to finalize direct message feature Minor bug fix for user profile/login/register improvement Prepare for Presentation and Documentations | Some documentations need to be updated due to grading criteria and feedback from iteration 2 | Improve SPPP, SDD documentations | 7 - Update documentations | 4
13 | 12/8 - 12/10 | 5 | 5 | 0 | 5 - Team Management 6 - Review Github 7 - Final Writeup/Release | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | Finalize Documentations | - | - | - | -

## Subhajit (Jeet)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader, backend Dev team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 09/14-09/27 | 8.5 | 7 | 1.5 | 0 - learned git and unit test cases, read several tutorials 1 - define high level requirements, 5 - make Backend Dev plan, send reminders to team members, 6 - set up git, local development 7 - research similar products, prepare presentation, did research on how other products work | 3.5 | 1 |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
3 | 09/29 - 10/05 | 5.5 | 4 | 1.5 | 2 - Designed basic db schema for post API 6 - Bought domain and set- it up 7 - research about Auth0 |  |  | 2 |  |  |  | 1 | 1 | 1. Designed DB schema 2. Bought domain to make it live on the internet and set it up on the server | 1. Designing DB schema for such large project was hard and had to do a lot of project 2. Communication among Backend team members was little unclear | 1. Finished DB schema with other backend team members 2. started doing a small backend team stand-up meeting, so everyone understands their responsibilities | 0 - Start implementing Auth0 1 - Start designing user post API | 6
4 | 10/06 - 10/12 | 8.5 | 7 | 1.5 | 0 - Learn more about Auth0 and how to use it 2 - Fixed some DB schema desgin flaw 3 - Started implementing Django application and folder structure | 2 |  | 2 | 3 |  |  |  |  | 1. Gave other backend team member a quick workshop about DB schema and REST apis 2. Assigned tasks to backend team members to work on 3. Finished set-up backend app with Django | 1. had to slow down the development because of diverse skill level of other team members. 2. It took a lot of time to do research on Auth0 and how to integrate with our app | 1. Developement speed is on right space now 2. Understood basics of Auth0 and how to use it | 1. Implementation of Auth0 to perform login and logout 2. Deployment to server to make it live online | 6
5 | 10/13 - 10/19 | 7 | 5.5 | 1.5 | 0 - Learned how to implement Auth0 3 - Implemented Auth0 4 - Performed manual Testing on Login and Logout 5 - Had a meeting about our deliverables and our tech backlogs | 1 |  |  | 3 | 1 | 0.5 |  |  | 1. Fixed last minutes bug for demo 2. Helped creating presentation slides 3. Participated in class presentation | 1. Auth0 integration is not working with backend APIs. 2. Deployment issue, unexpected error 3. Issue connecting server with clients | 1. Changed plan for Auth0, integrated in client side of code 2. Deployement issue is still there, need more time to debug it and fix it 3. Server - client connection is still there, need time to fix it | 1. Finish user post API 2. Designed standard system to deployment, no issue will occur in last time 3. Set-up Github auto merge, deployement test check tools 4. Set-up Staging, so we don't have to test on production | 12
6 | 10/20 - 10/26 | 7.5 | 6 | 1.5 | 0 - Learned Django JWT authentication 1 - Analyzed User Registration feature requirements 5 - Communicated about iteration deliverables and backlogs | 3 | 2 |  |  |  | 1 |  |  | - Fixed previous iteration bugs - Discussed about Backend deliveriables and backlogs | - issue connecting web app client with backend | - Left it as a backlog since it's not affecting development process | 1. Implementing Login API 2. Perform Manual testing on it | 6
7 | 10/27 - 11/02 | 7.5 | 6 | 1.5 | 0 - Learned about SimpleJwt Lib and it's usage 1 - Created DB table for Users and implemented Login API | 2 | 4 | [6 empty] | - User Login POST API is working - Setup production DB on the supabase Cloud | - issue connecting web app client with backend - JWT decode issue with Django | - Left it as a backlog since it's not affecting development process - have to do reasearch on the issue | 1. Design and Implementing User Registration | 5
8 | 11/03 - 11/08 | 7.5 | 6 | 1.5 | 3 - Implemented user Registration and Product API 6 - Configure server to accept request from Client |  |  |  | 5 |  |  | 1 |  | - User Registration POST API - Helped creating presentation slide - perticipated in class presentation | - Some issue with frontend code API request that is not going though banckend | - This will be our priority task for next iteration | 1. creating Delete Post, Update post API 2. Creating bookmark feature 3. Creating forget password feature | 6
9 | 11/09 - 11/24 | 4.5 | 3 | 1.5 | 3 - Fix the Refresh Token issue 6 - Configure server to accept request from Client |  |  |  | 2 |  |  | 1 |  | - Fix user relogin and refrsh token issue - Fix server client issue | No isses | NA | 1. create all product APIs
10 | 11/25 - 11/30 | 7.5 | 6 | 1.5 | 3 - Implemented create product, get all Products and get one product feature 4 - Wrote unit test cases for authentication |  |  |  | 4 | 2 |  |  |  | - Now we have APIs to create and get products from databases - Wrote unit test cases for authentication so it has production level code | 1. Forget password API is not working | Will fix forget password API first as 1st priority | - fix previous issuse - Help Aishwarya to write APIs - help Xantus to deploy app on vercel | 8
11 | 12/01 - 12/07 | 10 | 8.5 | 1.5 | 3 - Fix Previous Issue, created update product APIs 6 - Review pending PRs 7 - Help Aishwarya to build APIs, helped creating presentaions, participated in presentaion |  |  |  | 3 |  |  | 0.5 | 5 | - Fix issues and created update product API - Help creating presentations - Helped Aishwarya to understand and build APIs - Reviewed and merged existing PRs | 1. README needs to updated with all available APIs 2. Post Proudct Cloudinary issue (minor) | will fix everything before submitting the project | - Recheck everything one more time - merge PRs if there is any | 3
12 | 12/08 - 12/10 | 4 | 4 |  | 3 - updated main branch with latest be branch and fix some issue in frontend code |  |  |  | 4 |  |  |  |  | - updated main branch with updated code for final project submission | No isses | NA | NA | NA

## Aishwarya
Your Lead Roles: Configuration Management/ Product Management
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 09/22-09/27 | 7.5 | 5.5 | 2 | 0 - Learn git 5 - Product Management 6 - Setup Git and github version control tools, other specific tools like IDE,CI/CD and branching features 7 - Presentation, researched similar products. | 3 |  |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. keep a reminder and confirm 2. complete assignments and tracking team members | 0 - learn Django 1 - Implement while learning 2 - Brush up Python 5 - Complete assigned task | 8
3 | 09/29 - 10/05 | 8.5 | 6.5 | 2 | 0-Learn Reactt, Brushed up Python and earn Django 1-User Stories 2-Design Landing page 7-Research Landing page | 5 | 0.5 | 0.5 |  |  |  |  | 0.5 | 1.Write User Stories 2.Research Landing page | 1. Unclear with concepts of Django 2. Communication among Backend team members was little unclear |  | 1. Make clear about Django concepts 2. Complete task assignments 3. Developing Landing Page | 8
4 | 10/06 - 10/12 | 8.5 | 7 | 1.5 | 0. Brushed up Python, learn Django 3. Added content to Landing Page 7. Finalized content for Landing Page | 5 |  |  | 1 |  |  |  | 1 | 1. Created the Landing Page |  | 1. Completed the Landing Page 2. Learning Django but not completely familiar with it. 3. Write user stories for iteration 1 | 1-Write user stories( Non functional) 2-Continue learning Django | 8
5 | 10/13 - 10/19 | 4.5 | 3.5 | 1 | 0. Django tutorial 1. User Stories 7. User stories write-up(Non-functional) | 2 | 0.5 | [5 empty] | 1 | 1. Wrote the Non functional User Stories | No prior experience in deployment with API | 1. Done writing user stories( Non functional) 2.Write the content for Email verification 3.Research on 'Resend' an Email API | 1-Write the content for Email verification 2-Research and write content on 'Resend' an Email API and go through API tutorials. | 6
6 | 10/20 - 10/26 | 7.5 | 6 | 1.5 | 0. Django tutorial 1. go through User Registration feature requirements 5. Managed the newly created featues | 3 | 2 |  |  |  | 1 |  |  | -Created user info get API -Discussed backend deliverables and backlogs | Faced decode issue with django | Research on the issue | Performing Testing to setup new contribution standard | 6
7 | 10/27 - 11/02 | 7.5 | 6 | 1.5 | 0 Learned Django 3 implemented user info API | 2 |  |  | 4 |  |  |  |  | -Setup new contibution standard -user Login POST API is working | Decode issues with django | Research on the issue | configure server client connection and document the code | 5
8 | 11/03 - 11/08 | 7.5 | 5 | 1.5 | 3 Implemented new contribution standard |  |  |  | 5 |  |  |  |  | -configured server client connection -Documeted server side code -Participated in class presentation | Connection problem with Frontend API | work on the problem to fix APIs | Create Delete post Update post API | 6
9 | 11/09 - 11/17 | 8.5 | 7 | 1.5 | 0 Learned DRF framwork 3 Implementing User Registration REST API 5 Exisitng PR review | 1 |  |  | 3 |  | 3 |  |  | - Worked in building auth system with jeet - Implement Delete Product REST API - learned how to do PR review and reviewed a few PRs | No Issues | Research about the endpoints to handle user registration request and database to store user Information. | Planned to work on user Registration REST API To work on User Profile Info REST API | 7
10 | 11/18 - 11/24 | 7.5 | 6 | 1.5 | 0 learned Custom Model view of Django 3 Implemented Delete product API 5 Updated task status | 1 |  |  | 3 |  | 2 |  |  | - updated tasks - Implemented User Registration REST API | No Issues | Research about the User Profile Info REST API | To work on User Profile Info REST API | 8
11 | 11/25 - 11/30 | 9 | 8 | 1 | 3 Implementing User Profile Info REST API 5 Team management followup and PR review 6 Created task issues and assigned to team members |  |  |  | 3 |  | 3 | 2 |  | - Created task for team to focus on - Implemented User Profile Info REST API | No Issues | Research about the email restriction (bu email only) | To work on Email Restriction part | 7
12 | 12/1 - 12/7 | 8 | 7 | 1 | 3 Implementing BU Email Restriction and Forget password 6 Updated pull request and issues 7 Prepare presentation for Iteration 3 |  |  |  | 2 |  |  | 2 | 3 | - Created and updated tasks - Implemented Email restriction and forget password features. - Prepare for presentation and Documents - Partcipated in Iteration 3 presentation | Some documents need to be updated due to the feedback from previous iteration | Improve Documents | Update Documents | 8
13 | 12/8 - 12/10 | 4 | 4 |  | 7 Final check, writeup and release | [7 empty] | 4 | Finalize Documentations

## Nidhi
Your Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6 | 4 | 2 | 0. Learn Git and Django 6. Set up git 7. SPPP writeup | 3 | [5 empty] | 0.5 | 0.5 | 1. Write 1 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Not Familiar with Django 2. Not familiar with Cypress | 1. Finish going through Django tutorials 2. Complete task assignments 3. Familiarize myself with Cypress 4. Start implementing Django while learning | 0 - Continue to learn Django 1 - Implement while learning 2 - Brush up Python 3 - Familiarize myslf with Cypress 4 - Complete assigned task | 8
3 | 9/29-10/5 | 8.5 | 6.5 | 2 | 0. Learn Django, Brushed up Python, learn React 1. User Stories 2. UI for Landing Page 7. Research on landing page and Content for Landing page | 5 | 0.5 | 0.5 |  |  |  |  | 0.5 |  | 1. Not entirely familiar with React but making progress | 1. Finish going through Django tutorials 2. Complete task assignments 3. Familiarize myself with Cypress 4. Start coding for Landing Page | 0 - Continue to learn Django 1 - Implement while learning 2 - Brush up Python 3- Create the Landing Page 4- Start going through Cypress tutorials | 8
4 | 10/6-10/12 | 8.5 | 7.5 | 1.5 | 0. Brushed up Python, learn React, Cypress Tutorial 2. Update design for Landing Page 3. Landing Page | 4.5 |  | 0.5 | 2 |  |  |  |  | 1. Coding for the Landing page | 1. Currently learning Cypress by following tutorials, but not yet completely familiar with it 2. Created the Landing page but needs to be updated later according to the final design | 1. Started going through Cypress tutorials 2. Completed the Landing Page 3. Finished with the Django tutorials 4. Write user stories for iteration 1 | 0 - Continue with Cypress tutorials 3- Write the user stories(Functional) and their Acceptance Criteria | 4
5 | 10/13-10/19 | 5 | 4 | 1 | 0. Cypress tutorial 1. User Stories 7. Class diagram, User stories write-up (Functional and Acceptance Criteria) | 2 | 0.5 | [5 empty] | 1.5 | 1. Wrote the User Stories(Functional) and their Acceptance Criteria. 3. Participated in Iteration 1 presentation | 1. No prior experience in writing and deploying APIs | 1. Finish going through Cypress tutorials 2. Done writing user stories(Functional) and Acceptance Criteria 3. Write the content for Verificaton Email 4. Research on 'Resend' an Email API | 0 - Finish going through Cypress tutorial and start testing 1 - Go through API tutorials 2 - Write the Verification email content 3- Research on 'Resend' an email API | 6
6 | 10/20-10/26 | 7 | 5 | 2 | 0. Cypress Tutorial, Django API tutorials 7. Email templates | 4.5 | [6 empty] | 0.5 | 1. Email Template Design | No issues | 1. Finished learning Cypress 2. Template for email | 0 - Start testing 1 - Go through API tutorials 2 - Research on 'Resend' an email API | 7
7 | 10/27-11/2 | 8 | 6 | 2 | 0. Learn Djanjo API 4. write test code | 3 |  |  |  | 3 |  |  |  | 1. Wrote test code | No issues | 1. Currently learning APIs 2. Writing test code for component testing | 0 - continue testing 1 - Go through API tutorials 2 - Research on 'Resend' an email API | 7
8 | 11/3-11/9 | 6 | 4 | 2 | 4. write and update previous test code |  |  |  |  | 4 |  |  |  | 1. Wrote test code | No issues | 1. Finished learning APIs 2. Writing test code for component testing | 0 - continue testing 1 - Research on 'Resend' an email API | 7
9 | 11/18 - 11/24 | 5.5 | 4.5 | 1 | 3. Login to Mrketplace 4. Modified test code |  |  |  | 0.5 | 4 |  |  |  | 1. Modified Test Code 2. Fixed Login to Marketplace | No issues | 1. Modified Component testing code | 0 - Write e2e test cases and coninue adding component tests | 6
10 | 11/25 - 11/30 | 6 | 5 | 1 | 4. Write and Modify previous test code |  |  |  |  | 5 |  |  |  | 1. Wrote e2e test cases | No issues | 1. Wrote e2e testing code | 0 - Write e2e test cases and do Manual testing of new features | 8
11 | 12/1 - 12/7 | 8.5 | 7.5 | 1 | 4. Manual and e2e Testing of new feature 7. Updated STD and Presentation |  |  |  |  | 5.5 |  |  | 2 | 1. Updated STD and Testing part of Presentation 2. Performed Manual and Automation testing 3. Participate in Iteration 3 presentation | No issues | 1. Done writing testing code | 0 - Perform Final Testing | 3
12 | 12/8 - 12/10 | 2 | 2 |  | 4. Testing |  |  |  |  | 2 |  |  |  | 4. Modified Test Code and Performed Final Testing(Manual) | No issues | 1 - Perform Final Testing(Manual)

## Vedant
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/21 - 9/28 | 5.5 | 4.5 | 1 | 0 - learn git and react, started learning through a playlist 1 - Stated high level requirements 6 - set up git 7 - Prepared the two parts in spp document for overview and requirements | 3 | 0.5 |  |  |  |  | 0.5 | 0.5 | 1. Wrote 2 sections of SPPP 2. Set up git, commit a test message on git | 1. not familar with React framework, it's been a couple of years since I did programming so catching up to it | 1) Started with a playlist on YouTube for react, able to write a very basic code | Continue to learn React and get more familiar with it. | 7
2 | 9/29 - 10/5 | 5 | 4 | 1 | 0 - Learning React 2 - Designing UI mockup 3 - Started coding for basic login page | 3 |  | 0.5 | 0.5 | [5 empty] | 1. Not entirely familiar with react but catching up pretty quick. | 1) Able to write a basic code, planning to work on the login page implementation | 1) Continue to learn React and work on User story and design | 6
3 | 10/6 - 10/12 | 5 | 4 | 1 | 0- Learning React (Built small programs) 3 - Coded the login page | 1.5 |  |  | 2.5 |  |  |  |  | 1 - Coding the login page | 1 - Faced some complexities with the login page but gradually looked for tutorials | 1 - Able to make basic programs, learning more about React and learning to code more efficiently | 1 - Will work on UI and wireframe again for better design | 5
4 | 10/13 - 10/19 | 6.5 | 5.5 | 1 | 0 - Learning React and moved to better programs 2 - Designed mockups for other pages 3 - Recoding the login page as a pop up to the main landing page 7 - class diagram help | 1 |  | 0.5 | 3.5 |  |  |  | 0.5 | 1 - Design mockups for other pages 2 - Redoing the login page as a pop up to the main landing page | 1 - Trying to connect the login page as a pop up to main landing page, working on it currently. | 1 - Will complete the login page as a pop up to the main landing page | 1 - Learn react with more modules from the udemy course I am learning from. | 5
5 | 10/20 - 10/27 | 9 | 8 | 1 | 0 - Learning some new techniques in React 2 - Designed the new UI for login, registration, Marketplace and main page. 3 - Coding for registeration page addition to login pop up, coding the marketplace UI and post UI with create post pop up window 4 - Performed a few manual testing | 0.5 |  | 1 | 6 | 0.5 |  |  |  | 1 - Coding for the registeration page with marketplace page UI and implementation and post UI coding and implementation as well as create post UI and implementation. | 1 - Full connection between FE and BE is pending | 1 - Will complete the create post coding pop up window | 1 - Will complete the create post coding pop up window and try to start implementation for search bar | 6
6 | 10/28 - 11/4 | 7 | 6 | 1 | 0 - Learnt the search feature optimisation techniques for implementing it in project 2 - Designed UI for User profile page and about and contact pages 3 - Coding for search feature started | 1 |  | 1 | 4 |  |  |  |  | 1 - Completed the post creation pop up implementation. | 1 - Search feature optimisation is pending | 1- Will complete the search feature and try to contribute towards comment feature if time permits | 1 - Implementation of search engine and start comment feature | 7
7 | 11/5 - 11/10 | 7.5 | 5.5 | 2 | 2 - Optimised the design for the search feature 3 - Coding for the search feature 7- Worked on SDD SA architecture part |  |  | 0.5 | 4.5 |  |  |  | 0.5 | 1 - Completed the search feature implementation for frontend 2 - Worked on SDD SA architecture part | 1 - After logging in, the user should be directed to marketplace page 2 - If user deletes any post(product), the user should be directed to marketplace page whereas right now it directs the user showing no products found. 3 - If we create a user with the same email which is already in the BE, then it should throw an error | We will work upon new configurations and additions to the project in Iteration 3 | 1 - Designing and implementing the chat feature | 6
8 | 11/11 - 11/17 | 9.5 | 8.5 | 1 | 1 - Requirement analysis for the components required to be added to the filters. 2 - Designing the filter UI for the search and designing the update post UI 3 - Coding for the search feature optimization to include filters, coded for the post view for a better UI |  | 0.5 | 1 | 7 |  |  |  |  | 1- Partially completed the search feature by adding filters. 2 - UI and code fixes for post | 1 - Faced issues with setting up the filters. After coding and while testing, I wasn't able to use many filters at a time | 1 - Planning to correct the issue regarding multiple filters at a time. | 1 - Design UI for update post. Plan to design the UI for the direct message feature and plan to complete the filters feature | 5
9 | 11/18 - 11/24 | 5 | 4 | 1 | 2 - Design the Direct message functionality, design the update post feature functionality 3 - Completed the filters for the search feature |  |  | 1 | 3 |  |  |  |  | 1 - UI for direct message functionality 2 - Completed the filters | 1 - No issues found this week | 1 - Next, Nick would be covering the direct message functionality and next task is to connect BE to the current(recent) FE code. Once, that is completed, we will review and work upon new functionalities. | 1 - We plan to complete the connection of both FE & BE for the current code. | 5
10 | 11/25 - 11/30 | 3 | 2 | 1 | 2 - Updated design for the direct message functionaility 3 - Designed the update post feature with Steve |  |  | 0.5 | 1.5 |  |  |  |  | 1 - Completed UI for direct message 2 - Worked upon design for update post feature with Steve | 1 - No issues found this week | 1 - Plan to work on the presentation as well as check with nick regarding Direct message feature | 1 - Plan to complete the direct message feature and get everything in check for frontend for iteration3 | 4
11 | 12/1 - 12/7 | 5 | 4 | 1 | 3 - Worked on some part of web socket for the direct message feature with Nick and steve, worked on bug fixes 7 - Worked on the presentation design for iteration 3 Worked on the demo video for iteration 3 |  |  |  | 3 |  |  |  | 1 | 1 - Worked on the presentation for iteration 3 in terms of FE 2 - Completed the direct message feature | 1 - No issues found this week | 1 - Plan to work on contributing towards the writeups | 1 - Completing the writeups and submitting the documents with code on 10th | 3

## Xiancheng Yin(Xanthus)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 8 | 6.5 | 1.5 | 0 - learn git and django, read several tutorials 1 - define high level requirements through similar products, 5 - team meeting 6 - set up git 7 - research similar products, prepare presentation | 1.5 | 1.5 |  |  |  | 1.5 | 0.5 | 3 | 1. suggestions made by comparing similar products for high-level requirements and functionalities 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 0. not familar with Django framework, tried learning resources to see which is good 2. Sometimes communication is not clear. Task assignments is not clear. | 0. finish Django tutorial in 2 weeks, be able to create Djano project in online courses next week 2. Enforce communication, confirm everything. | 0 - continue to learn Django 1 - continue to define product name/ requirements 3 - seting up domain and Backend Code(documentation if time is permit) cowork with jeet | 7
3 | 9/29 - 10/5 | 8 | 6.5 | 1.5 | 0 - learn domain and Django and related things 1 - continue to define product name/ requirements 3 - seting up domain and Backend Code(documentation if time is permit) cowork with jeet 5 - team meeting, BE team meeting; | 1.5 | 1 |  | 2 |  | 2 |  |  | cowork with jeet seting up things | no issue |  | 0 - learn supabase and django; 3 - implementing supabase, create account, setting up, create tables and testing data; 5 - team meeting, BE team meeting; | 6.5
4 | 10/6 - 10/12 | 8 | 6.5 | 1.5 | 0 - learn supabase and django; 3 - implementing supabase, create account, setting up, create tables and testing data; 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | Set up Supabase account, created tables according to the attributes and functions for classes | no issue |  | 0 - learn database connecting related python; 3 - implementing settings.py, models.py, routers.py 5 - team meeting, BE team meeting; | 6.5
5 | 10/13 - 10/19 | 8 | 6.5 | 1.5 | 0 - learn database connecting related python; 3 - implementing settings.py, models.py, routers.py 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | Created settings.py, models.py, routers.py files, | no issue |  | 0 - learn database connecting related python; 3 - create product table migration 5 - team meeting, BE team meeting; | 6.5
6 | 10/20 - 10/26 | 8 | 6.5 | 1.5 | 0 - learn database connecting related python; 3 - create product table migration 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | create product table migration | no issue |  | 0 - Django Rest-framwork to create rest APIs (Learning); 3 - create product table migration 5 - team meeting, BE team meeting; | 6.5
7 | 10/27 - 11/3 | 8 | 6.5 | 1.5 | 0 - Django Rest-framwork to create rest APIs (Learning); 3 - create product table migration 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | create product table migration | no issue |  | 0 - Django Rest-framwork to create rest APIs (Learning); 3 - Webapp deployment to Vercel 5 - team meeting, BE team meeting; | 6.5
8 | 11/3 - 11/10 | 8 | 6.5 | 1.5 | 0 - Django Rest-framwork to create rest APIs (Learning); 3 - Webapp deployment to Vercel 5 - team meeting, BE team meeting; | 1.5 |  |  | 3 |  | 2 |  |  | Webapp deployment to Vercel | no issue |  | 1 - code smell analysis for product; 3 - changed product id to uuid, and improved referenced ID; start Creating product REST APIs and Cloudinary CD; 5 - communication with teammates | 5
9 | 11/10 - 11/17 | 3.5 | 3 |  | 1 - code smell analysis for product; 3 - changed product id to uuid, and improved referenced ID; start Creating product REST APIs and Cloudinary CD; 5 - communication with teammates |  | 0.5 |  | 2.5 |  | 0.5 |  |  | changed product id to uuid, and improved referenced ID; | no issue |  | 1 - requirement review for APIs and cloudinary cdn; 3 - Creating product REST APIs and Cloudinary CD 5 - communication with teammembers; | 5
10 | 11/17 - 11/24 | 4.5 | 3.5 |  | 1 - requirement review for APIs and cloudinary cdn; 3 - Creating product REST APIs and Cloudinary CD 5 - communication with teammembers; |  | 1 |  | 2.5 |  | 1 |  |  |  | no issue |  | 0 - learning testing by reviewing related documents 3 - Creating product REST APIs and Cloudinary CDN 4 - unit test on product for creation, get(read), modification and deletion; 5 - communicate with backend team for project progress and presentation 7 - prepare presentation | 10
11 | 11/24 - 12/1 | 10.5 | 9.5 |  | 0 - learning testing by reviewing related documents 3 - Creating product REST APIs and Cloudinary CDN 4 - unit test on product for creation, get(read), modification and deletion; 5 - communicate with backend team for project progress and presentation 7 - prepare presentation | 1 |  |  | 1.5 | 3 | 1 |  | 4 | product REST APIs and Cloudinary CDN; | no issue |  | 0 - learning testing by reviewing related documents 1 - code smell analysis for testing code; 4 - unit test on product for creation, get(read), modification and deletion; 5 - communicate with backend team for project progress and presentation 7 - practice presentation with teammates; | 5
12 | 12/1 - 12/8 | 5.5 | 3.5 |  | 0 - learning testing by reviewing related documents 1 - code smell analysis for testing code; 4 - unit test on product for creation, get(read), modification and deletion; 5 - communicate with backend team for project progress and presentation 7 - practice presentation; | 0.5 | 1 |  |  | 1 | 1 |  | 2 | unit test on product; | no issue

## Chenyang Lyu
Your Lead Roles: FE Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 5 | 5 | 1 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 2 | 1 |  |  |  |  | 1 | 1 | "1. make the ux frame 2. submit git files 3. Participate in Iteration 0 presentation" | the task assignment is not very clear | finish the ux design | -2 doing the ux design | 6
3 | 9/29 - 10/5 | 8 | 6.5 | 1.5 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 1.5 | 1 |  | 2 |  | 2 |  |  | Keep doing the ux design | no issue |  | 6- set up environment | 6.5
4 | 10/6 - 10/12 | 8 | 6.5 | 1.5 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 1.5 |  |  | 3 |  | 2 |  |  | doing sign up page front end code | no issue |  | 7- code writing | 6.5
5 | 10/13 - 10/19 | 8 | 6.5 | 1.5 | 0 - Learn with react 3 - Finish the login page and search features | 1.5 |  |  | 5 |  |  |  |  | finish sign up page and main page of the front end | no issue |  | 3- code writing | 6.5
6 | 10/28 - 11/4 | 7 | 4 | 1 | 2- Coding for the contact and about pop-up features 7- Revert the wrong coding | 3 | [6 empty] | 1 | Start the code of contact and about features | The code from last week is completely unuseable, redo the task |  | 1 - Finish the contact and about features, start comment feature | 5
7 | 11/5 - 11/10 | 6 | 4 | 1 | 3 - Coding with the contact and about features 3 - Coding for the comment feature |  |  |  | 4 |  |  |  |  | Completed the about and contact feature in the frontend | no issue | change the look of some features and keep working on the comment feature | 3- code writing for comment or chat features | 5
8 | 11/11 - 11/17 | 5 | 4 | 1 | 3 - Coding with the contact and about features 3 - Coding for the comment feature |  |  |  | 4 |  |  |  |  | Edit the about and contact feature in the frontend |  |  | 3- code writing for email message sending feature | 6
9 | 11/18 - 11/24 | 6 | 5 | 1 | 3 - Coding with the contact and about features 3 - Coding for the comment feature |  |  |  | 5 |  |  |  |  | coding for email sending feature |  |  | 3- code writing for comment or chat features | 6
10 | 11/25 - 11/30 | 7 | 6 | 1 | 3 - Coding for direct message feature |  |  |  | 6 |  |  |  |  | Edit the direct message feature in the frontend |  |  | 3- code writing for comment or chat features | 6
11 | 12/1 - 12/7 | 9 | 7 | 1 | 3 - Coding for direct message feature |  |  |  | 7 |  |  |  |  | Completed the direct message feature in the frontend

## studentName-Template
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6