## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration. | [5 empty] | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 9/14/2023 - 9/28/2023 | Project write-up proposal/ Team work-distribution, User requirement | None Tech issue so far | None non-tech issue so far | Next week : 1.User Requirement analysis 2.Final UXUI Design 3.BE Kickstart -> Schema + Login/Logout 4.FE Kickstart -> UI User Login/Logout/Home | 0 | 0 | 0 | 0 | 0 | 34.5 | 30.5 | 4 | 15 | 3.5 | 0 | 0 | 0 | 3 | 4.5 | 4.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Theerarun (Steve)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader, Backup Frontend
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6.5 | 4.5 | 2 | 0 - Learn git 1 - Define user requirement 5 - Team Management 6 - Setup Git 7 - Presentation/Writeup | 0.5 | 1 |  |  |  | 1 | 0.5 | 1.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. First-meetup is so good, we are missing people and late 2. communication is not enough. task assignment is not clear | 1. keep a reminder and confirm 2. Send task assignments to confirm with members and set up task-board | 0 - Learn Github Project/Issues 0 - Brushup React/JS 1 - Final User Requirement 2 - Work with Design Lead for UXUI 5 - Follow up each team 6 - Setup config/ implementation environment | 8
3 | 9/29 - 10/6 |  |  | 2

## Subhajit (Jeet)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/22-09/27 | 8.5 | 7 | 1.5 | 0 - learned git and unit test cases, read several tutorials 1 - define high level requirements, 5 - make Backend Dev plan, send reminders to team members, 6 - set up git, local development 7 - research similar products, prepare presentation, did research on how other products work | 3.5 | 1 |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Aishwarya
Your Lead Roles: Configuration Management/ Product Management
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/22-09/27 | 7.5 | 5.5 | 2 | 0 - Learn git 5 - Product Management 6 - Setup Git and github version control tools, other specific tools like IDE,CI/CD and branching features 7 - Presentation, researched similar products. | 3 |  |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP + Presentation Slides 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Setup Meeting | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. keep a reminder and confirm 2. complete assignments and tracking team members | 0 - learn Django 1 - Implement while learning 2 - Brush up Python 5 - Complete assigned task | 8

## Nidhi
Your Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 6 | 4 | 2 | 0. Learn Git and Django 6. Set up git 7. SPPP writeup | 3 | [5 empty] | 0.5 | 0.5 | 1. Write 1 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Not Familiar with Django 2. Not familiar with Cypress | 1. Finish going through Django tutorials 2. Complete task assignments 3. Familiarize myself with Cypress 4. Start implementing Django while learning | 0 - Continue to learn Django 1 - Implement while learning 2 - Brush up Python 1 - Familiarize myslf with Cypress 5 - Complete assigned task | 8

## Vedant
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/21 - 9/28 | 5.5 | 4.5 | 1 | 0 - learn git and react, started learning through a playlist 1 - Stated high level requirements 6 - set up git 7 - Prepared the two parts in spp document for overview and requirements | 3 | 0.5 |  |  |  |  | 0.5 | 0.5 | 1. Wrote 2 sections of SPPP 2. Set up git, commit a test message on git | 1. not familar with React framework, it's been a couple of years since I did programming so catching up to it | 1) Started with a playlist on YouTube for react, able to write a very basic code | Continue to learn React and get more familiar with it. | 7

## Chenyang Lyu
Your Lead Roles: FE Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2023-01-02 | 9/14 - 9/28 | 5 | 5 | 1 | 0 - learn git 1 - make sure the basic ux frame 2- make the rational diagram 6 - set up basic environment 7 - research similar products, prepare presentation 6. Set up git 7. SPPP writeup | 2 | 1 |  |  |  |  | 1 | 1 | "1. make the ux frame 2. submit git files 3. Participate in Iteration 0 presentation" | the task assignment is not very clear | finish the ux design | -2 doing the ux design | 6

## studentName-Template
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6